## Sheet7
Risk | Priority
Might not be finished on time | 3
Performance | 4
Might have trouble getting in contact with customer (Dr. Banks) because he’s very busy | 2
Uncertainty with requirements for finalized project | 1
Getting access to required Vue lessons since they cost real life money | 3
Only half the team has any experience with html or CSS prior to the class | 3
Team doesn’t have any prior Vue experience | 2
Might not be able to get a hosting server | 4
Unexpected expansion of project scope | 4
Team might not be able to fully learn and implement Vue | 2
Cutoff: >2

## Sheet1
Risk Information Sheet
Risk ID: 1 | Date: 2/3/2020 | Prob: 35% | Impact: High
Description:
Might have trouble getting in contact with Dr. Banks as he's the head of the department and thus can be very busy.
Refinement/context:
He could be out of his office. He may only be free when members of the team are busy.
Mitigation/monitoring:
Keep up with emails regularly. Plan meetings far in advance.
Management/contingency plan/trigger:
Schedule a meeting for another time. Try to get questions answered through email even though meeting in person would be ideal.
Current status: No issues thus far.
Originator: Entire team |  | Assigned to: Current Scrum Master

## Sheet2
Risk Information Sheet
Risk ID: 2 | Date: 2/3/2020 | Prob: 80% | Impact: Critical
Description:
Dr. Banks is unsure of final requirements for the project.
Refinement/context:
Dr. Banks doesn't know whether we will be able to have access to certain sensitive systems, including the login credentials database or have access to a document database.
Mitigation/monitoring:
Meet with Dr. Banks as frequently as possible to try and get more of the requirements for the project as we progress.
Management/contingency plan/trigger:
Proceed with the project as planned. Try to schedule another meeting. Adapt project if requirements change.
Current status: No issues thus far.
Originator: Entire team |  | Assigned to: Entire team

## Sheet5
Risk Information Sheet
Risk ID: 3 | Date: 2/3/2020 | Prob: 60% | Impact: High
Description:
No one on our team has any prior experience in the javascript framework Vue that the project will be based in.
Refinement/context:
Vue is new so none of us have used it before. Because of this, we must first learn how to use it before being able to fully implement it into our project.
Mitigation/monitoring:
Dr. Banks has offered us all subscriptions to access a Vue training program, so we will all use that program.
Management/contingency plan/trigger:
We would either have to switch the javascript framework to something else, or use regular javascript. Alternatively we could try to learn about Vue using sources other than the training program.
Current status: No issues thus far.
Originator: Entire team |  | Assigned to: Entire team

## Sheet6
Risk Information Sheet
Risk ID: 4 | Date: 2/3/2020 | Prob: 30% | Impact: High
Description:
Our team may have trouble fully learning how to use and implement Vue into our project.
Refinement/context:
Our team may not fully understand the training program provided to us by Dr. Banks.
Mitigation/monitoring:
Ask professors in the department if they have any Vue experience.
Management/contingency plan/trigger:
Search for our questions online, or switch to another javascript framework.
Current status: No issues thus far.
Originator: Entire team |  | Assigned to: Current Scrum Master